## Timeline
Week | Title | Difficulty level | Description | Due Date | Status | Comments
1 | Complete Requirements Document | Medium | Finalize the document and get sign off from instructor | sep 25th | In progress | Get feedback from instructor
2 | Complete Technical barriers assessment document | High | Finalize the document and get sign off from instructor | sep 25th | In progress | Get feedback from instructor
3 | complete Figma User Testing | Medium | Finalize the document and get sign off from instructor | sep 25th | In progress | Get feedback from instructor
4 | start building frontend | Medium | Connect wordpress to the hosting provider. | 2024-09-25 | In progress | Get feedback from instructor
5 | Continue building the backend |  | Develop the features of the website mentioned in the requirement document. | oct oct 8th | In progress | Get feedback from instructor
6 | Present the project |  | Finalize the product and present to the insrtructor | Oct 16th | In progress | Get feedback from instructor
7
| Presentation | Easy | Complete project presentation requirements. |  | Not started
Note on B1: SWD: What is the component you are working on?
Note on C1: SWD: What is your perception of how difficult this component will be? Easy ¦ Medium ¦ Difficult
Note on D1: SWD: A brief description of the tasks for this component.
Note on E1: SWD: Your target date for completion
Note on F1: SWD: Not Started In Progress Stalled Completed
Note on G1: SWD: Notes or reminders concerning this component.